## Sheet1
| PROJECT NAME | PROJECT DURATION | PROJECT START DATE | PROJECT END DATE
| 2 Step Authentication |  | January 17 2022
Task ID | Task Description | Task Duration | Start Date | End Date
1 | Project 1 | 48 | 2022-01-17 | 2022-03-06
2 | Project 2 | 48 | 2022-03-14 | 2022-05-01
3 | Project 3 | 48 | 2022-05-09 | 2022-06-26
Task ID | Project 3 Week 1 | Task Duration | Start Date | End Date
1.1 | Start Report | 4 | 2022-05-09 | 2022-05-13
1.2 | Include Curveball | 3 | 2022-05-13 | 2022-05-16
1.3 | Aquire Dongle | 2 | 2022-05-16 | 2022-05-18
1.4 | Initiate Dongle Testing | 21 | 2022-05-18 | 2022-06-08
1.5 | Finalise Testing Signoff | 5 | 2022-06-08 | 2022-06-13
1.6 | Deliver Implement Project | 13 | 2022-06-13 | 2022-06-26
Formulas:
PROJECT END DATE = [PROJECT START DATE]+[PROJECT DURATION]
PROJECT END DATE = [PROJECT START DATE]+4
PROJECT START DATE = [PROJECT END DATE, row above]